## White Label Setup Tasks
Category | Task | Task Description | Responsibility | Status | Integrator Contact Name | Integrator Contact Email | Datman Owner | Notes / Comments
Payment Page | Provide payment domain | Share the domain or subdomain that will host the white-labelled payment page (e.g., payments.example.com). | Integrator
Payment Page | Provide DNS CNAME record | Datman will generate and share the CNAME record required to map the payment domain to Datman infrastructure. | Datman
Payment Page | Configure DNS CNAME record | Add the CNAME record provided by Datman to your DNS provider and ensure DNS propagation is complete. | Integrator
Payment Page | Verify domain configuration | Validate that the payment domain resolves correctly to Datman systems after DNS configuration. | Datman
Apple Pay | Provide Apple Pay verification file | Provide the Apple Pay domain verification file required to enable Apple Pay on the payment domain. | Datman
Apple Pay | Host .well-known verification file | Upload the Apple Pay verification file to the /.well-known/ directory on the payment domain over HTTPS. | Integrator
Apple Pay | Confirm file accessibility | Ensure the Apple Pay verification file is publicly accessible without authentication or redirects. | Integrator
Apple Pay | Complete Apple Pay domain verification | Submit the domain verification request to Apple and complete the Apple Pay approval process. | Datman
Google Pay | Capture checkout screenshots | Capture screenshots of the checkout flow as required for Google Pay verification. | Datman
Google Pay | Submit verification details | Submit checkout details and supporting materials to Google Pay for review. | Datman
Google Pay | Complete Google Pay activation | Complete Google Pay approval and activate Google Pay on the payment page. | Datman